## RA_TEMPLATE
|  |  |  | DoVID2020 |  |  |  |  | QEHS Records / Data
Risk Assessment for DoVID20 Band Roadshow
Dept: |  | Sound |  |  | Team Leader: | Samuel Leong(Production Manager/Systems engineer) |  |  | Approved by HoD
Activity / Event name: |  | Band Roadshow |  |  | Team Member: | Lim Teh Beng (Crew Lead) |  |  | Name:
Location: |  | HillV2 Central Plaza Atrium |  |  |  | Tan Ah Gau (Crew) |  |  | Designation:
Effective Date: |  | 1st-June-2020 |  |  |  | Tan Jin Swee (Crew) |  |  | Evidence of Approval:
Event Start Date: |  | 4th-August-2020 | [6 empty] | <embed HOD approval email>
Event End Date: |  | 4th-August-2020
| Aspect / Hazard Identification |  |  | Impact / Risk Evaluation |  |  |  | Impact / Risk Control
S/N | Activities | EHS Aspects / Hazards | EHS Impact / Consequence | Existing Control Measures | Likelihood of Occurrence | Severity of Consequence | Initial Priority No. | Additional Controls (if any) | Implementation Person | Due Date | Status
1 | Preparation and packing of equipment to venue | Physical Hazard: Knocking against one another (people) | Cause injury, cuts and abrasions. | Getting the crew to move in an orderly fashion. | Low | Moderate | P4 | Place notices or limit the number of people within a tight space. | Lim | 2020-08-03 | In Progress
|  | Physical hazard: Sharp edges of equipment | Cause injury, cuts and abrasions. | Ensure crew have PPE on at all times | Low | Moderate | P4 | Check crew whether they have PP. Wear Long pants ALL crew | Samuel | 2020-08-04 | In Progress
|  | Physical Hazard: Equipment dropping from shelf | Cause death or serious crush Injury | Ensure crew have PPE on at all times | Low | High | P4 | All crew to Purchase Hard Hats to prevent head injury | Samuel | 2020-08-03 | Nil
|  | Egronomic Hazard (Fatigue) | Cause Injuries | Get the crew to have aqaquate breaks and rest | Low | Moderate | P4 | Water points to be added. Break times to be planned out. | Samuel | 2020-08-03 | In Progress
|  | Egronomic Hazard (Poor setup) | Cause Muscle Injury or Strain | Get the crew to use the right tools and make their work area more Ergronomic. | Moderate | Moderate | P2 | Crew to have a Basic toolkit. Have the equipment withing reach. | Lim | Nil | Nil
|  | Vehicle Accident | Loss of equipment and crew | Speed limit for the driver | Low | Low | P4 | Ensure that drivers have adaquate rest and book the logistics company 1 month in advance | Samuel | 2020-07-04 | Done
2 | Loading and Unloading | Physical Hazard: Equipment falls when unloading | Damage to equipment Injury to crew | Crew to Wear Covered shoes. (Steel Cap boots if avaliable) Get Backup equipment | Low | Moderate | P4 | All involved in loading activities are to wear appropriate PPE No loading of equipment in wet weather Before moving heavy equipment have at least 1 other person to help | Samuel | 2020-07-20
|  | Physical Hazard: Slipping when unloading/loading | Damage to equipment Injury to crew | Steel Caped Boots. No worn off sole. | Low | Moderate | P4 | Check crew whether their soles are worn out. Crew to have PPE Worn when entering venue. | Samuel | 2020-08-03 | In progress
|  | Egronomic Hazard: Back Injurt from heavy weight | Damage to equipment Injury to crew | Stretch before lifting and get more than 1 person to help when lifting objects >20KG | Low | High | P3 | Train the Crew to use the knees up to lift objects and not the back. | Samuel | 2020-08-01 | In progress
Samuel
Samuel
|  | Tripping over Cables, Carpats etc… | Damage to equipment Injury to crew | Check surrounding before heading anywhere. | Low | Moderate | P4 | Ensure that proper cable management is done and labelling of places to be done correctly. Use red tape or yellow and plack to signal caution when entering the are. | Samuel | 2020-08-01 | In progress
3 | Bump in | Physical Hazard: Equipment may drop onto crew when setting up | Damage to equipment Injury to crew | Equipment and Crew may be injured (toe injury, etc) | Low | High | P3 | Have at least 2 person when setting up heavy equipment such as speakers, Monitors, staging & lighting. PPE to be worn at all times when rigging | Samuel | 2020-08-03 | In progress
|  | Physical Hazard: Sharp corners might cause crew to be hurt | Injury to crew(cuts, Abrasions,etc) | Ensure that ALL CREW wear PPE when Bumping in or Out | Low | High | P3 | Have a medical team (paramedic) team backstage to support if pre-hospital care required.Book them 1 month in advanced | Samuel | 2020-07-03 | Done
|  | Physical Hazard: Working in low/bright light Areas can cause crew to miss their step | Injury to crew(cuts, falls,etc) | Ensure that ALL CREW wear PPE when Bumping in or Out Crew to have a torchlight with them Crew to carry test pens to test for electricity | Moderate | Moderate | P2 | Have external lights to light up the dimly lit area. (Get contractors) Wear Shades | Samuel | 2020-07-03 | Done
|  | Physical Hazard: Rigging speakers | Cause Muscle Injury or Strain | Have a buddy system when setting up of speakers | Moderate | Moderate | P2 | Stretch/ Warm up before rigging Teach crew how to properly carry the speakers | Samuel | 2020-08-03 | In progress
|  | Safety hazard: Wet weather during setup | Electrocution, falls. Damge to crew and equipment | Check weather radar every 2 hours. Stop Work when thunderstorm or heavy rain | Low | High | P3 | Get a tentage setup In case venuse gets wet. FOH also needs tentage. Trunking for all cables. Crew to have Poncho or at least umbrella. | Samuel | 2020-07-03 | Done
|  | Safety hazard: Hot weather during setup | Ultraviolet rays may cause crew to have sun burn or irritation | Wear long sleeve shirts when setting up or those fake tattoo sleeve. | Low | Low | P4 | Regular water breaks to prevent dehydration or heat stroke. | Samuel | 2020-08-03 | In Progress
|  | Safety Hazard: Frayed electrical cables | Electrocution, falls. Damge to crew and equipment | Have a electrician or CEW to rig and check | Low | High | P3 | Testpen before working. Crew to do a sweep to see if the area has any loose wire hanging. No metal objects on stage | Samuel | 2020-08-03 | Nil
4 | Rehearsal | Physical Hazard: Exposed to loud Noises constantly (>85dB) | Damage to crew hearing | Have crew to have earplugs or IEMS to protect their ears. | Low | High | P3 | When testing or ringing out stage, Get crew to direct public away and stay away whehn testing. Have signages | Samuel | 2020-08-03 | Nil
|  | Safety Hazard: Cables not gaffed down properly | Tripping, falls. Damage to crew and Artists. | Safety OIC to do a sweep before soundcheck begiins to make sure | Low | High | P3 | Nil | Samuel | 2020-08-04 | Nil | Nil
|  | Safety Hazard: Electrical sockets overloading | Electrocution, falls. Damge to crew and equipment | Follow Power Diagram and not overload anything. | Moderate | High | P2 | Use current and voltage meter to double check. | Samuel | 2020-08-04 | Nil
|  | Safety Hazard: Tripping off stage | Serious injury to crew and artist | Use a reflective tape to highlight the edges and end of stage | Low | High | P3 | Have the stage Tech before soundcheck to breif the band on the layout and where the edges are | Tan Jin Swee | 2020-08-04 | Nil | Nil
|  | Safety Hazard: Stage collaspe | Serious injury to crew and artist | get a engineer to vet through the stage setup. If using risers, have proper weight | Low | High | P3 | Nil | Samuel | 2020-07-04 | Nil | Nil

## Risk Matrix
Severity | Very High | High | Moderate | Low | Very Low
Likelihood
Very High | Intolerable Risk | Intolerable Risk | Substantial Risk | Tolerable Risk | Tolerable Risk
| (P1) | (P1) | (P2) | (P4) | (P4)
High | Intolerable Risk | Substantial Risk | Moderate Risk | Tolerable Risk | Tolerable Risk
| (P1) | (P2) | (P3) | (P4) | (P4)
Moderate | Substantial Risk | Moderate | Moderate Risk | Tolerable Risk | Tolerable Risk
| (P2) | Risk | (P3) | (P4) | (P4)
(P3)
Low | Tolerable Risk | Tolerable Risk | Tolerable Risk | Tolerable Risk | Trivial Risk
| (P4) | (P4) | (P4) | (P4) | (P5)
Very Low | Tolerable Risk | Tolerable Risk | Tolerable Risk | Trivial Risk | Trivial Risk
| (P4) | (P4) | (P4) | (P5) | (P5)